## Read Me
Requirements Traceability Matrix — ChurnGuard R1
Document ID: RTM-CG-001 ¦ Version 1.0 ¦ Owner: Shubham Tiwari, Senior Business Analyst
Project: ChurnGuard — churn-risk detection and retention workflow, B2B SaaS for e-commerce sellers
Purpose
Proves that every business requirement is realised in a functional requirement, specified in the FSD,
built from a user story, tested, accepted in UAT and signed off. Read left to right for forward
traceability; filter any column to trace backwards from a test or a story to its business driver.
Sheets
RTM — one row per functional requirement, with its full trace chain.
Coverage Summary — live formulas counting requirements, test coverage and pass rate per business requirement.
Source documents
BRD-CG-001 Business Requirements Document (BR IDs)
FRD-CG-001 Functional Requirements Document (FR IDs)
FSD-CG-001 Functional Specification Document (FSD Ref column)
US-CG-001 User Stories and Acceptance Criteria (US IDs)
UAT-CG-001 UAT Plan and Sign-off Pack (UAT scenario IDs)
Conventions
A functional requirement may appear against more than one business requirement where it serves both;
FR-041, FR-045 and FR-051 each appear twice for that reason.
SIT Status and UAT Status are set from executed test evidence, never assumed.
'Pass with S4 open' means accepted with a low-severity defect logged and scheduled — see Defect Ref.
Status in the final column is a formula: Closed only when both SIT and UAT have passed.
Note
Portfolio sample. Requirement content reflects real delivery practice; account volumes, thresholds
and metrics are illustrative and anonymised.

## RTM
BR ID | Business Requirement | Priority | FR ID | Functional Requirement | FSD Ref | User Story | Test Case ID | Test Type | SIT Status | UAT Scenario | UAT Status | Defect Ref | Status
BR-01 | Single, consistently calculated churn-risk score per high-value account, refreshed daily | Must | FR-011 | Calculate composite score as weighted sum of five sub-scores, 0-100 | FSD 3.1 | US-03 | TC-001 | Functional | Pass | UAT-01 | Pass |  | Closed
BR-01 | Single, consistently calculated churn-risk score per high-value account, refreshed daily | Must | FR-014 | Complete a full scoring cycle daily within the batch window | FSD 2 | US-01 | TC-002 | Functional / Performance | Pass | UAT-01 | Pass |  | Closed
BR-01 | Single, consistently calculated churn-risk score per high-value account, refreshed daily | Must | FR-015 | Allow on-demand rescore of a single account | FSD 5.1 | US-15 | TC-003 | Functional | Pass | UAT-07 | Pass |  | Closed
BR-02 | Score derived from five weighted signals: usage, marketplace health, support, commercial, engagement | Must | FR-001 | Retrieve product usage metrics, 30d and 90d windows | FSD 3.2 | US-02 | TC-004 | Interface | Pass | UAT-02 | Pass |  | Closed
BR-02 | Score derived from five weighted signals: usage, marketplace health, support, commercial, engagement | Must | FR-002 | Retrieve marketplace connector health and store performance | FSD 3.3 | US-02 | TC-005 | Interface | Pass | UAT-02 | Pass |  | Closed
BR-02 | Score derived from five weighted signals: usage, marketplace health, support, commercial, engagement | Must | FR-003 | Retrieve support metrics: volume, priority, SLA breaches, reopens, CSAT | FSD 3.4 | US-02 | TC-006 | Interface | Pass | UAT-02 | Pass |  | Closed
BR-02 | Score derived from five weighted signals: usage, marketplace health, support, commercial, engagement | Must | FR-004 | Retrieve commercial data: plan, seats, failed payments, invoice ageing, renewal | FSD 3.5 | US-02 | TC-007 | Interface | Pass | UAT-02 | Pass |  | Closed
BR-02 | Score derived from five weighted signals: usage, marketplace health, support, commercial, engagement | Must | FR-005 | Retrieve engagement data: last activity, QBR attendance, champion status, response rate | FSD 3.6 | US-02 | TC-008 | Interface | Pass | UAT-02 | Pass |  | Closed
BR-02 | Score derived from five weighted signals: usage, marketplace health, support, commercial, engagement | Must | FR-010 | Calculate a 0-100 sub-score per signal using the banded rules | FSD 3.2-3.6 | US-02 | TC-009; TC-010 | Functional / Data reconciliation | Pass | UAT-02 | Pass |  | Closed
BR-03 | Accounts classified into agreed risk tiers; tier movement detected and retained | Must | FR-016 | Assign risk tier from composite using configured boundaries | FSD 3.7 | US-03 | TC-011 | Functional | Pass | UAT-03 | Pass |  | Closed
BR-03 | Accounts classified into agreed risk tiers; tier movement detected and retained | Must | FR-017 | Compare new tier with previous and classify the movement | FSD 3.7 | US-04 | TC-012 | Functional | Pass | UAT-03 | Pass |  | Closed
BR-03 | Accounts classified into agreed risk tiers; tier movement detected and retained | Must | FR-018 | Apply configurable hysteresis buffer at each tier boundary | FSD 3.7 | US-04 | TC-013; TC-014 | Functional / Boundary | Pass | UAT-03 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-021 | Create a Retention Task on escalation into Watch or Critical | FSD 5.2 | US-08 | TC-015 | Functional | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-022 | Task carries score, tier change, dominant driver, top three signals, deep link | FSD 5.2 | US-08 | TC-016 | Functional | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-023 | Set due date from tier SLA on the CS business calendar | FSD 4.4 | US-09 | TC-017 | Functional / Boundary | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-024 | Notify CS Manager on a Stable-to-Critical move in one cycle | FSD 4.4 | US-09 | TC-018 | Functional | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-025 | Route to CS Manager queue where no active owning CSM exists | FSD 4.4 | US-09 | TC-019 | Functional / Negative | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-026 | Prevent duplicate tasks for the same account and tier; update instead | FSD 4.4 | US-08 | TC-020 | Functional / Negative | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-028 | Record first touch and elapsed business time | FSD 4.4 | US-10 | TC-021 | Functional | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-029 | Mark SLA breached and notify the CS Manager | FSD 4.4 | US-10 | TC-022 | Functional | Pass | UAT-05 | Pass |  | Closed
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | FR-030 | Suppress alerting during the configured shadow-run period | FSD 8 (M-4) | US-12 | TC-064 | Functional / Cutover | Pass | UAT-01 / CU-3 | Pass |  | Closed
BR-05 | Each alert carries a retention playbook selected from the dominant risk driver | Must | FR-013 | Identify dominant risk driver and two next contributors | FSD 3.1 | US-03; US-11 | TC-023 | Functional | Pass | UAT-06 | Pass |  | Closed
BR-05 | Each alert carries a retention playbook selected from the dominant risk driver | Must | FR-027 | Attach playbook mapped to the dominant driver from configuration | FSD 4.5 | US-11 | TC-024 | Functional | Pass | UAT-06 | Pass |  | Closed
BR-06 | CSM can see which signals drove the score, with underlying values and comparison period | Must | FR-012 | Record sub-score, raw inputs and comparison period for every signal | FSD 4.2 | US-02; US-14 | TC-025 | Functional | Pass | UAT-07 | Pass |  | Closed
BR-06 | CSM can see which signals drove the score, with underlying values and comparison period | Must | FR-031 | Present a risk panel on the Account record | FSD 5.1 | US-13 | TC-026 | Functional / Usability | Pass | UAT-07 | Pass |  | Closed
BR-06 | CSM can see which signals drove the score, with underlying values and comparison period | Must | FR-032 | Show each signal with sub-score, contribution, inputs and period | FSD 5.1 | US-14 | TC-027; TC-028 | Functional / Usability | Pass | UAT-07 | Pass |  | Closed
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | FR-035 | Provide a one-step action to open a pre-populated retention case | FSD 5.1 | US-16 | TC-029 | Functional | Pass | UAT-08 | Pass |  | Closed
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | FR-036 | Retention Case object with opening score, driver, playbook, owner, outcome | FSD 4.3 | US-16 | TC-030 | Functional | Pass | UAT-08 | Pass |  | Closed
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | FR-037 | Support the six defined case statuses | FSD 4.3 | US-17 | TC-031 | Functional | Pass | UAT-08 | Pass |  | Closed
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | FR-038 | Require a controlled closure reason before any Closed status | FSD 6 (V-03, V-04) | US-17 | TC-032 | Functional / Negative | Pass | UAT-08 | Pass |  | Closed
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | FR-039 | Prevent more than one open case per account | FSD 6 (V-05) | US-16 | TC-033 | Functional / Negative | Pass | UAT-08 | Pass |  | Closed
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | FR-040 | Auto-close as Saved after 30 consecutive Stable days unless on hold | FSD 4.3 | US-18 | TC-034 | Functional | Pass | UAT-08 | Pass |  | Closed
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | FR-041 | Link the case to the renewal outcome | FSD 4.3 | US-19 | TC-035 | Functional | Pass | UAT-08 | Pass |  | Closed
BR-08 | Leadership dashboard: tier mix, ARR at risk, SLA compliance, save rate | Must | FR-042 | Retention Health dashboard with tier, ARR, movement, cases, SLA, save rate | FSD 5.3 | US-20 | TC-036 | Functional / Reconciliation | Pass | UAT-09 | Pass |  | Closed
BR-08 | Leadership dashboard: tier mix, ARR at risk, SLA compliance, save rate | Must | FR-043 | Filter by team, CSM, plan, primary marketplace and date range | FSD 5.3 | US-21 | TC-037 | Functional | Pass | UAT-09 | Pass |  | Closed
BR-08 | Leadership dashboard: tier mix, ARR at risk, SLA compliance, save rate | Must | FR-044 | Critical worklist ordered by ARR descending | FSD 5.3 | US-21 | TC-038 | Functional | Pass | UAT-09 | Pass |  | Closed
BR-08 | Leadership dashboard: tier mix, ARR at risk, SLA compliance, save rate | Must | FR-045 | Show Critical-tier opening cohort split by final outcome | FSD 5.3 | US-22 | TC-039 | Functional / Reconciliation | Pass | UAT-09 | Pass |  | Closed
BR-08 | Leadership dashboard: tier mix, ARR at risk, SLA compliance, save rate | Must | FR-046 | Refresh daily after the cycle and display the last refresh timestamp | FSD 5.3 | US-20 | TC-040 | Functional | Pass | UAT-09 | Pass |  | Closed
BR-08 | Leadership dashboard: tier mix, ARR at risk, SLA compliance, save rate | Must | FR-047 | Export the current dashboard view subject to access rights | FSD 5.3 | US-21 | TC-041 | Functional | Pass | UAT-09 | Pass with S4 open | CG-121 | Closed
BR-09 | Score history retained 13 months for trend analysis and model tuning | Must | FR-019 | Write a dated score-history record every cycle | FSD 4.1 | US-05 | TC-042 | Functional | Pass | UAT-12 | Pass |  | Closed
BR-09 | Score history retained 13 months for trend analysis and model tuning | Must | FR-020 | Retain 13 months and archive rather than delete | FSD 4.1 | US-05 | TC-043 | Inspection | Pass | UAT-12 | Pass |  | Closed
BR-09 | Score history retained 13 months for trend analysis and model tuning | Must | FR-033 | Display a 90-day score trend on the risk panel | FSD 5.1 | US-15 | TC-044 | Functional / Usability | Pass | UAT-07 | Pass with S4 open | CG-118 | Closed
BR-10 | Weights, thresholds and SLAs adjustable by a business administrator without a code release | Must | FR-048 | Maintain signal weights; reject any set not totalling 100% | FSD 6 (V-01) | US-23 | TC-045 | Functional / Negative | Pass | UAT-10 | Pass |  | Closed
BR-10 | Weights, thresholds and SLAs adjustable by a business administrator without a code release | Must | FR-049 | Maintain tier boundaries, hysteresis and SLA durations | FSD 6 (V-02) | US-23 | TC-046 | Functional / Negative | Pass | UAT-10 | Pass |  | Closed
BR-10 | Weights, thresholds and SLAs adjustable by a business administrator without a code release | Must | FR-050 | Maintain driver-to-playbook mapping and closure reason list | FSD 4.5 | US-23 | TC-047 | Functional | Pass | UAT-10 | Pass |  | Closed
BR-10 | Weights, thresholds and SLAs adjustable by a business administrator without a code release | Must | FR-051 | Version every configuration change; apply forward only | FSD 4.5 | US-23; US-25 | TC-048 | Functional / Audit | Pass | UAT-10 | Pass |  | Closed
BR-10 | Weights, thresholds and SLAs adjustable by a business administrator without a code release | Must | FR-052 | Preview proposed configuration impact without saving | FSD 5.4 | US-23 | TC-049 | Functional | Pass | UAT-10 | Pass |  | Closed
BR-11 | Scoring suppressed and flagged where source data is stale or incomplete | Must | FR-006 | Resolve every source record to one Account ID; log exceptions | FSD 2 | US-06 | TC-050 | Functional / Negative | Pass | UAT-04 | Pass |  | Closed
BR-11 | Scoring suppressed and flagged where source data is stale or incomplete | Must | FR-007 | Mark a signal Insufficient Data on stale feed or >20% nulls | FSD 2 | US-06 | TC-051 | Functional / Negative | Pass | UAT-04 | Pass |  | Closed
BR-11 | Scoring suppressed and flagged where source data is stale or incomplete | Must | FR-008 | Suppress scoring where two or more signals are insufficient | FSD 6 (V-08) | US-07 | TC-052 | Functional / Negative | Pass | UAT-04 | Pass |  | Closed
BR-11 | Scoring suppressed and flagged where source data is stale or incomplete | Must | FR-009 | Redistribute weight where exactly one signal is insufficient | FSD 6 (V-07) | US-07 | TC-053 | Functional | Pass | UAT-04 | Pass |  | Closed
BR-11 | Scoring suppressed and flagged where source data is stale or incomplete | Must | FR-034 | Display data-quality status and unavailable signals on the panel | FSD 5.1 | US-07; US-15 | TC-054 | Functional / Usability | Pass | UAT-04 | Pass |  | Closed
BR-12 | Access follows the CRM role model; all changes auditable | Must | FR-056 | Restrict risk data visibility to the defined role matrix | FSD 7 | US-25 | TC-055 | Security | Pass | UAT-12 | Pass |  | Closed
BR-12 | Access follows the CRM role model; all changes auditable | Must | FR-057 | Write an immutable audit entry for every controlled change | FSD 7 | US-25 | TC-056; TC-057 | Security / Audit | Pass | UAT-12 | Pass |  | Closed
BR-12 | Access follows the CRM role model; all changes auditable | Must | FR-058 | Provide a filterable, exportable audit report | FSD 7 | US-25 | TC-058 | Functional | Pass | UAT-12 | Pass |  | Closed
BR-13 | CSM can record a justified tier override with reason and expiry | Should | FR-053 | Override a tier with reason, justification and expiry within 90 days | FSD 6 (V-06) | US-24 | TC-059 | Functional / Negative | Pass | UAT-11 | Pass |  | Closed
BR-13 | CSM can record a justified tier override with reason and expiry | Should | FR-054 | Show calculated and overridden tier; suppress alerts while active | FSD 5.1 | US-24 | TC-060 | Functional | Pass | UAT-11 | Pass |  | Closed
BR-13 | CSM can record a justified tier override with reason and expiry | Should | FR-055 | Expire the override automatically and resume alerting | FSD 4.1 | US-24 | TC-061 | Functional | Pass | UAT-11 | Pass |  | Closed
BR-14 | Predicted risk comparable against actual renewal outcome | Should | FR-041 | Link case to renewal outcome for accuracy analysis | FSD 4.3 | US-19 | TC-062 | Functional / Reconciliation | Pass | UAT-09 | Pass |  | Closed
BR-14 | Predicted risk comparable against actual renewal outcome | Should | FR-045 | Report opening-tier cohort against final outcome | FSD 5.3 | US-22 | TC-063 | Functional / Reconciliation | Pass | UAT-09 | Pass |  | Closed

## Coverage Summary
Requirements coverage summary — ChurnGuard R1
All figures are live formulas over the RTM sheet. A business requirement with zero test cases would show 0% and fail exit criterion X-7.
BR ID | Business Requirement | Priority | FRs mapped | With test case | SIT passed | UAT passed | UAT coverage % | Exit criterion X-7
BR-01 | Single, consistently calculated churn-risk score per high-value account, refreshed daily | Must | 3 | 3 | 3 | 3 | 100% | Met
BR-02 | Score derived from five weighted signals: usage, marketplace health, support, commercial, engagement | Must | 6 | 6 | 6 | 6 | 100% | Met
BR-03 | Accounts classified into agreed risk tiers; tier movement detected and retained | Must | 3 | 3 | 3 | 3 | 100% | Met
BR-04 | Owning CSM alerted automatically on escalation, with an SLA-bound due date | Must | 9 | 9 | 9 | 9 | 100% | Met
BR-05 | Each alert carries a retention playbook selected from the dominant risk driver | Must | 2 | 2 | 2 | 2 | 100% | Met
BR-06 | CSM can see which signals drove the score, with underlying values and comparison period | Must | 3 | 3 | 3 | 3 | 100% | Met
BR-07 | Every intervention recorded as a structured retention case closed with an outcome | Must | 7 | 7 | 7 | 7 | 100% | Met
BR-08 | Leadership dashboard: tier mix, ARR at risk, SLA compliance, save rate | Must | 6 | 6 | 6 | 6 | 100% | Met
BR-09 | Score history retained 13 months for trend analysis and model tuning | Must | 3 | 3 | 3 | 3 | 100% | Met
BR-10 | Weights, thresholds and SLAs adjustable by a business administrator without a code release | Must | 5 | 5 | 5 | 5 | 100% | Met
BR-11 | Scoring suppressed and flagged where source data is stale or incomplete | Must | 5 | 5 | 5 | 5 | 100% | Met
BR-12 | Access follows the CRM role model; all changes auditable | Must | 3 | 3 | 3 | 3 | 100% | Met
BR-13 | CSM can record a justified tier override with reason and expiry | Should | 3 | 3 | 3 | 3 | 100% | Met
BR-14 | Predicted risk comparable against actual renewal outcome | Should | 2 | 2 | 2 | 2 | 100% | Met
| Total — Release 1 |  | 60 | 60 | 60 | 60 | 100% | Met
Assumptions and sources
• Counts are derived from the RTM sheet only; nothing on this sheet is typed in by hand.
• 'Pass*' matches both 'Pass' and 'Pass with S4 open', per the UAT exit criteria: S4 defects may remain open with an agreed owner and date.
• Requirement rows and statuses were supplied by the project's SIT and UAT evidence packs (UAT-CG-001, sections 6 and 10).
• BR-15 is not listed: deferred to Release 2 and therefore out of R1 coverage.